## Sheet1
Type | Activity | Time
Architecture | Total | 49
| Checking out the database scheme for the 3rd form normalization (modifying if needed) | 2
| Creating initial Repository-class and Unit of work Façade for database operations | 4
| UI Web prototype with navigation scheme | 12
| Activity/Sequence UML-diagram for Admin-role | 3
| Activity/Sequence UML-diagram for Trainer-role | 3
| Activity/Sequence UML-diagram for Regular user role | 3
| Creating Notification interface | 3
| Synchronizing existing active directory entries | 4
| Refactoring HTTP controllers to keep up the low coupling, high cohesion for domain layers architecture | 15
Backend | Total | 46
| Creating raw SQL-script for database entities with parent/child relationship commands (Initial DDL-script) | 8
| Seeding the sample data for tables | 4
| Creating O/R mapping classes and initial debug/release configuration | 4
| Defining the primary auth-roles for code first authority system: Regular user->Trainer->Admin | 2
| Altering database-index for full text search support | 2
| Developing PDF/RTF template for generating certificates with signing | 16
| Creating user manager infrastructure for 3 roles | 10
Frontend | Total | 152
| Layout implementation for header according to UI-prototype | 2
| Layout implementation for middle according to UI-prototype | 4
| Layout implementation for footer according to UI-prototype | 1
| Layout implementation for menu/navigation according to UI-prototype | 2
| Developing index screen for Admin | 2
| Developing View trainings screen for Admin | 3
| Developing Add training screen for Admin | 3
| Developing Edit/Update training screen for Admin | 2
| Developing Report screen for Admin | 4
| Linking Report screen with actions | 2
| Adding UI for filter strategies – mapping them to URL route system | 6
| Linking Report screen with filter-actions | 2
| Creating CRUD screens for training instances | 6
| Linking admin screens with external API’s (GroupWise, ProjectXT) | 16
| Developing CRUD Training instance views | 6
| Developing View participations screen | 3
| Linking Trainer screens with HTTP controller | 2
| Developing CRUD screens for training ratings | 8
| Developing screen for viewing training requests by Admin | 3
| Adding UI controls for text search | 4
| Developing training list view for regular user | 3
| Adding UI controls for filtering training instances for regular user | 4
| Creating screen for viewing training instances for regular user | 3
| Adding UI controls for filtering training list | 4
| Developing screen for viewing users by regular user | 2
| Adding UI controls for filtering support | 4
| Developing wizard screen for participation request by regular user | 4
| Developing wizard screen for rate training workflow | 3
| Developing wizard screen for suggest training view | 3
| Developing view for generating certificate | 4
| Creating register view | 3
| Creating login view | 2
| Creating edit user credentials view | 4
| Developing CRUD-screens for user rights – for admin only | 8
| UI views improvements | 20
Middleware | Total | 85
| Developing HTTP-controller for admin screens activities | 4
| Adding delete HTTP-controller action | 1
| Adding report action to Admin HTTP-controller | 2
| Adding filter support to Admin HTTP-controller | 4
| Adding support for managing work packages via HTTP controller instance | 8
| Adding support for managing GroupWise appointments via HTTP controller instance | 8
| Adding actions to HTTP-controller for CRUD training instances | 6
| Developing HTTP controller for Trainer endpoint activities | 4
| Adding workflow action for Confirm->Request->notification for trainer participation screen | 4
| Creating HTTP controller for viewing training ratings with filtering support | 4
| Adding actions to admin HTTP controller for viewing training requests with filtering support | 4
| Creating HTTP controller for regular user actions | 4
| Adding filter strategies to regular user HTTP controller for viewing training instances | 4
| Creating HTTP controller for regular user’s training instance with filtering support | 4
| Developing HTTP controller for list user actions by regular user, with filtering support | 4
| Creating HTTP controller for certificate generator support | 6
| Developing HTTP controller for register view | 4
| Developing HTTP controller for login view | 2
| Developing HTTP controller for edit user credentials | 4
| Developing HTTP controller for user right manipulation activities | 4
Server | Total | 61
| Linking admin screens with HTTP-controller | 2
| Creating On Adding trigger to subscribe users | 3
| Implementing notification interface, linking dependency injected implementation with HTTP-controller | 4
| Adding 2 “export as” actions to Admin HTTP-controller – for excel and html formats | 8
| Link training ratings with HTTP controller | 2
| Link training requests screen with HTTP controller | 2
| Linking training list screen with HTTP controller | 2
| Linking training list screen with HTTP controller | 2
| Synchronize UI-filters with HTTP controller’s actions | 4
| Linking screen for viewing users with HTTP controller | 2
| Adding support for participation request with notification trigger | 4
| Adding Rate training workflow activities with notification trigger | 3
| Adding support for suggest training creation with notification trigger | 3
| Adding support for generating certificate by regular user | 6
| Linking regular user views with HTTP controller actions | 3
| Tuning up notification template for e-mail | 4
| Tuning claims and auth-filtering depending on user role rights | 4
| Linking regular user CRUD activities with HTTP controller | 3
Unit test | Total | 21
| Developing Unit test coverage for Admin HTTP-controller | 4
| Unit test coverage for recently developed controller actions | 6
| Coverage unit test for recently created controller actions | 11
| Unit test coverage | 4
UI Test | Total | 12
| Testing Admin screens UI | 2
| UI testing of recently created screens | 8
| UI testing for training list views | 2
Consolidation | Total | 28
| Review intermediate results | 14
| Corrections for the current iteration | 14
Deployment | Total | 26
| Aligning with Server PC requirements | 3
| Administrative activities for database server | 6
| Aligning with IIS/Apache requirements | 4
| Developing web deployment package for release | 5
| Deploying release and investigating fallbacks | 4
| Looking through HTTP speed performance and 4xx, 5xx HTTP-errors | 4
| Total estimation time | 480